## IE
{{CODE}} - INFORMATION EXCHANGE WORKSHEET (BEP Annexes 5-6)
Exchange | Milestone | Planned date | Container(s) | Purpose (PIM) | Information need (ISO 7817-1) | Geometry (LOD-like) | Information (data) | Documentation | Format | Responsible
E1 - Site / reference | M1 | {{M1_DATE}} | {{CODE}}-AR-* ref; {{CODE}}-GE-* | Coordination | Existing conditions | Massing / site | Plot data, boreholes | Survey, geotech report | IFC+PDF | EC / AR / GE
E2 - Structural concept | M2 | {{M2_DATE}} | {{CODE}}-{{OR}}-ZZ-M3-STR-0001; {{CODE}}-{{OR}}-ZZ-M3-STL-0001 | Coordination, verification | Concept structural sizing | Generic elements | Preliminary sections, materials | Concept calc note | RVT+IFC+PDF | {{MODELLER_S}} (Modeller / Calculist S)
E3 - Developed STR+HID | M3 | {{M3_DATE}} | {{CODE}}-{{OR}}-*-STR-*; {{CODE}}-{{OR}}-*-HID-* | Coordination, verification, quantities | Developed design | Detailed elements | Analytical results, loads, schedules | Calc reports, quantities | RVT+IFC+PDF | EC
E4 - Coordinated set | M4 | {{M4_DATE}} | {{CODE}}-{{OR}}-ZZ-M3-0001 federated | Coordination, quantities | Coordinated, clash-free | Coordinated elements | Zero unresolved clashes at M4 | Clash report, BCF | NWD/Revit+PDF | {{BIM_COORDINATOR}} (BIM Coordinator)
E5 - Construction docs | M5 | {{M5_DATE}} | {{CODE}}-{{OR}}-*-DR-*; {{CODE}}-{{OR}}-*-M3-* | Construction docs, asset (if req.) | For construction | Fabrication-ready detail | Final data set | Full drawing set + reports | RVT+IFC+PDF+DWG | EC

## MOD-development
{{CODE}} - Model information-need development per milestone
Model / Container | Discipline | M1 | M2 | M3 | M4 | M5 | Notes
{{CODE}}-{{ROW_OR}}-ZZ-M3-{{ROW_DISC}}-0001 | {{ROW_DISC}} | {{ROW_M1}} | {{ROW_M2}} | {{ROW_M3}} | {{ROW_M4}} | {{ROW_M5}} | {{ROW_NOTE}}

## Notes
{{CODE}} - IE Worksheet - Notes
Specify information need by purpose and exchange using ISO 7817-1:2024: geometrical, alphanumerical and documentary information. A single LOD number is insufficient.
Milestone dates M1-M5 belong to the information production schedule (0010 MIDP/TIDP) and BEP; do not invent dates here.
Acceptance criteria: correct naming, shared coordinates, LOIN met, zero unresolved clashes at M4.
All exchanges pass through the CDE (WIP -> Shared -> Published); externals via 01_Incoming (verify <=5 working days).
File size rule: no native .rvt over 300 MB (audit + purge first, split last resort with BEP change).