## Matrix
MODEL EXCHANGE FLOW MATRIX - {{PROJECT_NAME}} ({{CODE}})
Model / data drop | [5 empty] | INFORMATION SENDER (who issues) | [7 empty] | INFORMATION RECIPIENT (who receives) | [7 empty] | DELIVERABLE BIM USES BY PHASE
Container code | Data drop name | Date | Software origin | Software recipient | Format | ARC | STR | INS | QS | VIS | CRD | CON | CLI | ARC | STR | INS | QS | VIS | CRD | CON | CLI | ARC design | STR analysis | INS analysis | Cost/QTO | 3D coordination | 4D planning | Record model | Deliverable | FM
A - CONCEPT / ANTEPROYECTO (milestone M1 - {{M1_DATE}})
{{CODE}}-{{OR}}-ZZ-M3-ARC-0001 | Architectural concept model | {{M1_DATE}} | Revit | Arquimedes | IFC4 + PDF | X | [8 empty] | X |  | X |  | X | X | X | X | [6 empty] | X
B - DEVELOPED / PROYECTO BASICO (milestone M2 - {{M2_DATE}})
{{CODE}}-{{OR}}-ZZ-M3-STR-0001 | Structural developed model | {{M2_DATE}} | CypeCAD | Revit | IFC4 |  | X | [6 empty] | X |  |  | X |  | X |  |  |  | X |  |  | X
E - EXECUTION / PROYECTO DE EJECUCION (milestone M3 - {{M3_DATE}})
{{CODE}}-{{OR}}-ZZ-M3-STR-0002 | Structural execution model | {{M3_DATE}} | Revit | Robot | IFC4 + native |  | X | [9 empty] | X |  | X | X |  |  | X |  |  | X |  |  | X
{{CODE}}-{{OR}}-ZZ-M3-ZZZ-0001 | Federated coordination model | {{M3_DATE}} | Navisworks | Navisworks | NWD + BCF | [5 empty] | X |  |  | X | X | X |  |  |  | X | X |  |  |  |  | X | X
C - CONSTRUCTION / CONSTRUCCION (milestones M4-M5 - {{M4_DATE}} / {{M5_DATE}})
{{CODE}}-{{OR}}-00-DR-STR-0001 | Construction drawings set | {{M5_DATE}} | Revit | AutoCAD | DWG + PDF |  | X | [9 empty] | X |  |  | X | X |  |  |  | X |  |  |  | X
FM - OPERATION & MAINTENANCE / MANTENIMIENTO (post M5)
{{CODE}}-{{OR}}-ZZ-M3-ZZZ-0002 | As-built / record model | {{M5_DATE}} | Revit | OpenBIM/IFC | IFC4 | [5 empty] | X | [8 empty] | X | X | [6 empty] | X | X | X

## MOD
{{CODE}} - EXCHANGE FLOW MATRIX (BEP Annexes 3-4) - Model deliverables (MOD)
Container / Model | Discipline | Originator | Author (from) | Recipient (to) | Format | Purpose | Trigger / Milestone | CDE target state
{{CODE}}-{{OR}}-ZZ-M3-{{ROW_DISC}}-0001 {{ROW_ROLE}} model | {{ROW_ROLE}} | {{OR}} | {{ROW_PERSON}} (Modeller {{ROW_DISC}}) | {{BIM_COORDINATOR}} (BIM Coordinator); Client | Native RVT + IFC + PDF | Coordination, verification, quantities | At each data drop
{{CODE}}-AR-ZZ-M3-ARC-0001 Architecture reference | Architecture (A) | AR | External architecture office ({{AR_OFFICE}}) | EC (via 01_Incoming) | IFC + PDF (+ native if provided) | Reference for coordination | Before each data drop | 01_Incoming/Architecture -> 02_Shared/00_Architecture
{{CODE}}-GE-XX-RP-GEO-0001 Geotechnical report | Geotechnical (G) | GE | External geotechnical office ({{GE_OFFICE}}) | EC (via 01_Incoming) | PDF + data (CSV/DWG) | Foundation design input | Before M2 | 01_Incoming/Geotechnical-Borehole-Data -> 02_Shared
{{CODE}}-{{OR}}-ZZ-M3-ZZZ-0001 Federated model | Multi (Z) | EC | {{BIM_COORDINATOR}} (BIM Coordinator) | Client; task teams | NWD/Revit federation + clash report PDF | 3D coordination, clash detection | At each data drop M2-M5 | 02_Shared

## DOC
{{CODE}} - EXCHANGE FLOW MATRIX (BEP Annexes 3-4) - Document deliverables (DOC)
Document | ID | Author (from) | Recipient (to) | Format | Purpose | Trigger / Milestone
Professional Services Agreement | {{CODE}}-{{OR}}-XX-RP-ZZZ-0001 | EC | Client | DOCX/PDF | Contract | Project start
Annex A - BIM Protocol | {{CODE}}-{{OR}}-XX-RP-ZZZ-0002 | EC | Client | DOCX/PDF | Contractual BIM obligations | Project start
EIR | {{CODE}}-{{OR}}-XX-RP-ZZZ-0003 | EC on behalf of Client | Client (adopts) | DOCX/PDF | Information requirements | Project start
BEP | {{CODE}}-{{OR}}-XX-RP-ZZZ-0004 | {{BIM_MANAGER}} (BIM Manager) | Client; team | DOCX/PDF | Execution plan | Project start; revised on change
MIDP + TIDP | {{CODE}}-{{OR}}-XX-SP-ZZZ-0007 | {{INFO_MANAGER}} (Information Manager) | Client; team | XLSX | Delivery plan | Project start; updated per milestone
Container Register | {{CODE}}-{{OR}}-XX-SP-ZZZ-0008 | {{INFO_MANAGER}} (Information Manager) | Team (audit) | XLSX | Audit trail | Continuous
Calculation reports (S) | {{CODE}}-{{OR}}-XX-RP-STR-xxxx | {{CALC_STRUCTURAL}} (Structural calculist) | Client | PDF | Structural justification | M3-M5
Coordination report | {{CODE}}-{{OR}}-XX-RP-ZZZ-xxxx | {{BIM_COORDINATOR}} (BIM Coordinator) | Client; team | PDF | Clash results | Each data drop
Meeting minutes | {{CODE}}-{{OR}}-XX-RP-ZZZ-0010 | Meeting chair | Attendees | DOCX/PDF | Decisions + actions | Each meeting

## Codes
{{CODE}} - CODES LEGEND (Kickoff Standard Section 4)
Field | Code | Meaning
Naming format | MC-Originator-Level-Type-Discipline-Number_Status_Revision | Every information container
Originator | EC | {{AUTHOR}} (Lead Appointed Party)
Originator | AR | External architecture office ({{AR_OFFICE}})
Originator | GE | External geotechnical office ({{GE_OFFICE}})
Level | 00, 01... | Building level
Level | XX | No level (reports, schedules)
Level | ZZ | Multiple levels
Type | M3 | 3D model
Type | M2 | 2D file
Type | DR | Drawing
Type | RP | Report
Type | SP | Schedule/Spec
Type | CM | Communication
Discipline | STR | Structural - concrete
Discipline | STL | Structural - steel
Discipline | MAS | Structural - masonry
Discipline | FDN | Structural - foundations
Discipline | HID | Hydraulic
Discipline | FIR | Fire-fighting
Discipline | ELE | Electrical
Discipline | GEO | Geotechnical
Discipline | ARC | Architecture (reference)
Discipline | MEC | HVAC / mechanical
Discipline | ELV | Telecom / data
Discipline | DRA | Storm drainage
Discipline | GAS | Gas
Discipline | CIV | Civil / earthworks
Discipline | ROA | Roads / pavement
Discipline | ACO | Acoustics
Discipline | SUS | Sustainability / environmental
Discipline | TOP | Topography / survey
Discipline | CRD | Coordination (federated model + clash)
Discipline | ZZZ | Multi-discipline
Status | S0 | WIP
Status | S1 | Shared - coordination
Status | S2 | Shared - information
Status | S3 | Shared - review
Status | S4 | Shared - approval
Status | A | Published
Revision | P01, P02... | Preliminary
Revision | C01, C02... | Contractual / published